## Sheet2
Original Tax List |  |  |  | New Task List
Task | Start Date | End Date | Team Members | Task | Start Date | End Date | Team Members
Form Project Team | 2024-01-12 | 2024-01-17 | Sharvari with input from rest | Form Project Team | 2024-01-12 | 2024-01-17 | Sharvari with input from rest
Decide on Topic | 2024-01-17 | 2024-01-30 | All | Decide on Topic | 2024-01-17 | 2024-01-30 | All
Data Collection | 2024-01-17 | 2024-01-30 | All | Data Collection | 2024-01-17 | 2024-01-30 | Alicia, Namra, Shweta
Proposal Document | 2024-01-30 | 2024-02-25 | All | Proposal Document | 2024-01-30 | 2024-02-25 | All
Proposal Presentation Slides and Video | 2024-02-25 | 2024-02-28 | Alicia with input from rest | Proposal Presentation Slides and Video | 2024-02-25 | 2024-02-28 | Alicia with input from rest
Data Preparation and Cleaning | 2024-03-01 | 2024-03-05 | All | Data Preparation and Cleaning | 2024-03-01 | 2024-03-05 | All
Model Creation | 2024-03-05 | 2024-03-15 | All | Visualization | 2024-03-05 | 2024-03-15 | Shweta and Namra
Develop Plan for Visualization | 2024-03-15 | 2024-03-22 | All | ARIMA/Moving Avg Models | 2024-03-15 | 2024-03-22 | Sharvari
Progress Report | 2024-03-22 | 2024-03-29 | All | Demographic Relationships | 2024-03-22 | 2024-03-29 | All
Final Report | 2024-03-29 | 2024-04-19 | All | Progress Report | 2024-03-22 | 2024-03-29 | Alicia with input from rest
Poster | 2024-03-29 | 2024-04-19 | All | Final Report | 2024-03-29 | 2024-04-19 | All
|  |  |  | Poster | 2024-03-29 | 2024-04-19 | All

## Sheet3
Region | Correlation 1996-2021 | Correlation 2008-2021
Southeast Reliability Corporation (SERC) | -0.6301 | -0.8804
Midwest Reliability Organization (MRO) | -0.2946 | -0.8117
Northeast Power Coordinating Council (NPCC) | -0.8612 | -0.9271
Reliability First Corporation (RFC) | -0.8562 | -0.9284
Western Electricity Coordinating Council (WECC) | -0.2282 | -0.6884
Texas Regional Entity (TRE) | 0.0282 | 0.7115

## Sheet1
Region | Selected Model
SERC Reliability Corporation (SERC) | Exponential smoothening with smoothening level 0.2
Midwest Reliability Organization (MRO) | Exponential smoothening with smoothening level none
Northeast Power Coordinating Council (NPCC) | ARIMA (1,0,1)
Reliability First Corporation (RFC) | ARIMA (0,0,2)
Western Electricity Coordinating Council (WECC) | Exponential smoothening with smoothing level 0.5
Texas Regional Entity (TRE) | ARIMA (0,0,2)